## Guidelines
Reciprocal Exchange Work Plan Guidelines
*Read this page carefully before starting to complete your work plan.*
Please download this document to edit it. To download the document, go to "File" in the upper left hand corner, click "Download As," and select "Microsoft Excel (.xlsx)." *Please save the file consistently, including your names and project country.
U.S. Participants and Fellowship Alumni Collaborators must work together on this work plan. Finalized work plans for 2024 Reciprocal Exchanges must be submitted to IREX via Canvas at least 30 days prior to implementation, but we strongly encourage submitting deliverables as early as possible. Your deliverables must be approved before any project funds are spent, including booking travel. Any major changes to your project scope (including new dates) must be reviewed and approved by IREX and the U.S. Department of State prior to implementing any changes. Please ensure every day and activity is accounted for in this work plan. You may add rows to the template as needed.
Implementation Dates | Project implementation dates must be between January 15 - June 30, 2024.
Project Goal | Briefly describe the purpose of your project, including the knowledge, skills, or values you want your project to impart.
Planning, Implementation, and Wrap-Up Periods | Include all activities you will undertake to plan, implement, and conclude/share your project.
Location | Please list the exact location of each activity. For hybrid projects, please add the platform via which any virtual events will take place.
Activity Type | Broadly define the kind of activity taking place. Activity types may include meetings, lectures, trainings, film screenings, etc.
Activity Description | Describe what will take place during each activity.
Number, Type of Participants | Describe who will participate in each activity. Be as specific as possible (e.g., university undergraduates, elementary school teachers, local filmmakers, conference attendees, rural hospital staff, etc.). Please list the number of participants as exactly as possible. This is required and will be approved by U.S. Embassies prior to implementation.
Activity Outcome (Implementation Period only) | Complete this section for the Implementation Period only. Describe what you want participants to take away from each activity (e.g., increased knowledge about a country, a new skill, etc.).
Project Team/Stakeholders | List the individuals and/or organizations who will support implementation of your project activities.

## Work Plan Template
Reciprocal Exchange Award Work Plan
Project Title: |  | Project Goal:
U.S. Participant Name(s): |  | Project Description:
Fellowship Alumni Collaborator Name(s):
Fellowship Alumni Collaborator Country of Residence:
Project Format (In-person/hybrid):
Implementation Date(s):
Location (City/Cities, Country):
WORK PLAN
Date and Estimated Time | Location (City, State, Venue, or Virtual Platform) | Activity Type | Activity Description | Number and Type of Participants | Activity Outcome
Pre-Departure Planning Period
[At least 30 days prior to implementation] | Canvas | Grant Requirement | Submit updated work plan and budget to IREX with finalized implementation plans
In-Country Implementation Period
Within 48 hours of arrival in-country (if in-person) | City, U.S. Embassy/Consulate | Grant Requirement | Required security briefing with U.S. Embassy or Consulate | U.S. Participant & Fellowship Alumni Collaborator | Increased knowledge of safety and security environment in project host country.
Post-travel Wrap-Up Period
[Within 30 days of completed travel] | Online | Grant Requirement | Submit final report to IREX
PROJECT TEAM/STAKEHOLDERS
List the individuals and/or organizations who will implement the project and the roles they will play.
Individual/Organization Name | Title/Description | Role

## Example In-Person Work Plan
Reciprocal Exchange Award Work Plan
Project Title: | Ms. Megabyte Workshop: Internet Literacy Training for Girls in Nigeria | Project Goal: | To increase internet literacy of 50 teenage girls in Abuja and Lagos by implementing a 3-day computer skills workshop.
U.S. Participant Name(s): | Jane Doe | Project Description: | This project will increase the internet literacy and public speaking skills of 50 teenage girls in Abuja and Lagos, Nigeria through a 3-day workshop focusing on internet research. During this project, the girls will be introduced to relevant tools and resources, conduct internet research on a selected topic, and present on their topic. This project will inform Capital Start-up works of the Nigerian context and better position our team to work within diverse contexts and in communities with limited resources.
Fellowship Alumni Collaborator Name(s): | Chike Oladipo
Fellowship Alumni Collaborator Country of Residence: | Nigeria
Project Format (In-person/hybrid/virtual): | In-Person
Implementation Date(s): | August 1-15, 2022
Location (City/Cities, Country): | Lagos and Abuja, Nigeria
WORK PLAN
Date and Estimated Time | Location (City, State, Venue) | Activity Type | Activity Description | Number and Type of Participants | Activity Outcome
Pre-Departure Planning Period
Three months before travel | Oklahoma City | Stakeholder Meetings | Meeting with Capital Start-up Works to discuss details of collaboration | Jane Doe, Chike Oladipo (remote), 2 Capital Start-up Works staff
Two months before travel | Oklahoma City | Contract Signing | Finalize MOU with Capital Start-up Works | 2 Capital Start-up Works Staff, Jane Doe, Chike Oladipo (remote), 2 Nigerian Society of Engineers (NSE) staff
30 days prior to implementation | Canvas | Grant Requirement | Submit updated work plan and budget to IREX with finalized implementation plans | Jane Doe, Chike Oladipo
One month before travel | Abuja and Lagos, Nigeria | Event Promotion | Advertise workshop opportunity in Abuja and Lagos and collect workshop sign-ups | Chike Oladipo, Jane Doe (remote), 2 NSE staff
One month before travel | Oklahoma City | Curriculum Design | Create workshop curriculum in collaboration with Capital Start-up Works | Jane Doe, Chike Oladipo (remote), 2 Capital Start-up Works staff
One month before travel | Abuja and Lagos, Nigeria | Workshop Prep | Workshop logistics preparations (obtain space, arrange meals, design event promotion materials, etc.) | Chike Oladipo, 2 NSE staff
One month before travel | Oklahoma City --> Atlanta | Travel | Travel from Oklahoma City to Atlanta, GA to obtain Nigerian visa | Jane Doe
One month before travel | Oklahoma City | Travel Planning | Purchase flight, get vaccinations, make travel arrangements | Jane Doe
In-country Implementation Period
August 1-2, 2022 | Oklahoma City --> Lagos | Travel | Travel from Oklahoma City to Lagos, Nigeria | Jane Doe
2022-08-03 | Lagos, Nigeria | Planning Meetings | Workshop prep and meet and greet with Nigerian Society of Engineers (NSE) staff | Chike Oladipo, Jane Doe, 2 NSE staff | Completed lesson plans and materials
August 3, 2022 - 2:00pm | Lagos, Nigeria - U.S. Consulate | Grant Requirement | Required security briefing with U.S. Consulate in Lagos | Jane Doe | Increased knowledge of safety and security environment in project host country.
2022-08-05 | Lagos, Nigeria | Networking Day | Meetings with community leaders who work on girls' empowerment and computer literacy training | Jane Doe, Chike Oladipo, 5 Community Leaders | Increased understanding of local context
2022-08-06 | Lagos, Nigeria - P2P Co-working Space | Workshop | Workshop Day 1: Internet research concepts, research topic selection, basic computer/Internet usage techniques | Chike Oladipo, Jane Doe, 2 NSE staff, 25 girls ages 12-15 | Increased knowledge of how to do internet research
2022-08-07 | Lagos, Nigeria - P2P Co-working Space | Workshop | Workshop Day 2: Facilitated research on selected topics | Chike Oladipo, Jane Doe, 2 NSE staff, 25 girls ages 12-15 | Increased capacity to do internet research.
2022-08-08 | Lagos, Nigeria - P2P Co-working Space | Workshop | Workshop Day 3: Present research findings and record video of top 5 presentations | Chike Oladipo, Jane Doe, 2 NSE staff, 25 girls ages 12-15 | Increased public speaking and information synthesis capacity.
2022-08-08 | Lagos --> Abuja, Nigeria | Travel | Travel from Lagos to Abuja by air | Jane Doe, Chike Oladipo | N/A
2022-08-10 | Abuja, Nigeria - Nigerian Society of Engineers Office | Networking Day | Meetings with community leaders who work on girls' empowerment and computer literacy training | Jane Doe, Chike Oladipo, 5 Community Leaders | Increased understanding of local context
2022-08-11 | Abuja, Nigeria - Nigerian Society of Engineers Office | Workshop | Workshop Day 1: Internet research concepts, research topic selection, basic computer/Internet usage techniques | Chike Oladipo, Jane Doe, 2 NSE staff, 25 girls ages 12-15 | Increased knowledge of how to do internet research
2022-08-12 | Abuja, Nigeria - Nigerian Society of Engineers Office | Workshop | Workshop Day 2: Facilitated research on selected topics | Chike Oladipo, Jane Doe, 2 NSE staff, 25 girls ages 12-15 | Increased capacity to do internet research.
2022-08-13 | Abuja, Nigeria | Workshop | Workshop Day 3: Present research findings | Chike Oladipo, Jane Doe, 2 NSE staff, 25 girls ages 12-15 | Increased public speaking and information synthesis capacity.
2022-08-14 | Abuja, Nigeria | Debrief | Project team will debrief on lessons learned and plan Oklahoma City presentation outline | Chike Oladipo, Jane Doe, 2 NSE staff | Plan for next steps and outline for Capital Start-up Works presentation.
2022-08-15 | Abuja --> Oklahoma City | Travel | Travel from Abuja, Nigeria to Oklahoma City | Jane Doe | N/A
Post-travel Wrap-Up Period
2022-09-01 | Oklahoma City - Capital Start-up Works Office | Skills-sharing Event | Present videos and lessons learned to start-up employees working on computer literacy education at Capital Start-up Works event | Jane Doe, 50 start-up employees working on computer literacy education | Increased knowledge of Nigerian context.
By September 15, 2022 | Online | Grant Requirement | Submit final report to IREX | Jane Doe, Chike Oladipo
PROJECT TEAM/STAKEHOLDERS
List the individuals and organizations who will implement the project and the roles they will play.
Individual/Organization Name | Title/Description | Role
Jane Doe | Reciprocal Exchange Participant | Project Organizer
Chike Oladipo | Reciprocal Exchange Fellowship Alumni Collaborator Collaborator | Project Organizer
Capital Start-up Works | U.S. Partner Organization | Provide event space and curriculum development support
Nigerian Society of Engineers | Nigerian Partner Organization | Provide event space and networking support

## Example Hybrid Work Plan
Reciprocal Exchange Award Work Plan
Project Title: | Ms. Megabyte Workshop: Internet Literacy Training for Girls in Nigeria | Project Goal: | To increase internet literacy of 40 teenage girls in Abuja and Lagos by implementing a 3-day computer skills workshop.
U.S. Professional Name(s): | Jane Doe | Project Description: | This project will increase the internet literacy and public speaking skills of 50 teenage girls in Abuja and Lagos, Nigeria through a 3-day workshop focusing on internet research. During this project, the girls will be introduced to relevant tools and resources, conduct internet research on a selected topic, and present on their topic. This project will inform Capital Start-up works of the Nigerian context and better position our team to work within diverse contexts and in communities with limited resources.
Fellow Alumni Name(s): | Chike Oladipo
Fellowship Alumni Collaborator Country of Residence: | Nigeria
Project Format (In-person/hybrid/virtual): | Hybrid
Implementation Date(s): | August 1-15, 2022
Location (City/Cities, Country): | Lagos and Abuja, Nigeria
WORK PLAN
Date and Estimated Time | Location (City, State, Venue (address) or Virtual Platform) | Activity Type | Activity Description | Exact #, Type of Participants | Activity Outcome
Pre-Implementation Planning Period
Three months before implementation | Online | Stakeholder Meetings | Meeting with Capital Start-up Works to discuss details of collaboration | Jane Doe, Chike Oladipo, 2 Capital Start-up Works staff
Two months before implementation | Online | Contract Signing | Finalize MOU with Capital Start-up Works | 2 Capital Start-up Works Staff, Jane Doe, Chike Oladipo, 2 Nigerian Society of Engineers (NSE) staff
30 days prior to implementation | Canvas | Grant Requirement | Submit updated work plan and budget to IREX with finalized travel/project plans | Jane Doe, Chike Oladipo
One month before implementation | Abuja and Lagos, Nigeria | Event Promotion | Advertise workshop opportunity in Abuja and Lagos and collect workshop sign-ups | Chike Oladipo, Jane Doe, 2 NSE staff
One month before implementation | Online | Curriculum Design | Create workshop curriculum in collaboration with Capital Start-up Works | Jane Doe, Chike Oladipo, 2 Capital Start-up Works staff
One month before implementation | Abuja and Lagos, Nigeria | Workshop Prep | Workshop logistics preparations (obtain space, arrange meals, design event promotion materials, obtain PPE, etc.) | Chike Oladipo, 2 NSE staff
Implementation Period
2022-08-01 | Lagos, Nigeria - P2P Co-working Space | Networking Day | Meetings with community leaders who work on girls' empowerment and computer literacy training | Jane Doe (remote) , Chike Oladipo, 5 Community Leaders | Increased understanding of local context
2022-08-02 | Lagos, Nigeria - P2P Co-working Space | Workshop | Workshop Day 1: Internet research concepts, research topic selection, basic computer/Internet usage techniques | Chike Oladipo, Jane Doe (remote), 2 NSE staff, 25 girls ages 12-15 | Increased knowledge of how to do internet research
2022-08-03 | Lagos, Nigeria - P2P Co-working Space | Workshop | Workshop Day 2: Facilitated research on selected topics, presentation on the basics of coding | Chike Oladipo, Jane Doe (remote), Jenny Doe (remote) 2 NSE staff, 25 girls ages 12-15 | Increased capacity to do internet research, introduction to coding
2022-08-04 | Lagos, Nigeria - P2P Co-working Space | Workshop | Workshop Day 3: Present research findings and record video of top 5 presentations | Chike Oladipo, Jane Doe (remote), 2 NSE staff, 25 girls ages 12-15 | Increased public speaking and information synthesis capacity.
2022-08-05 | Abuja, Nigeria - Nigerian Society of Engineers Office | Networking Day | Meetings with community leaders who work on girls' empowerment and computer literacy training | Jane Doe (remote), Chike Oladipo, 5 Community Leaders | Increased understanding of local context
2022-08-06 | Abuja, Nigeria - Nigerian Society of Engineers Office | Workshop | Workshop Day 1: Internet research concepts, research topic selection, basic computer/Internet usage techniques | Chike Oladipo, Jane Doe (remote), 2 NSE staff, 15 girls ages 12-15 | Increased knowledge of how to do internet research
2022-08-07 | Abuja, Nigeria - Nigerian Society of Engineers Office | Workshop | Workshop Day 2: Facilitated research on selected topics, presentation on the basics of coding | Chike Oladipo, Jane Doe (remote), Jenny Doe (remote) 2 NSE staff, 15 girls ages 12-15 | Increased capacity to do internet research, introduction to coding
2022-08-08 | Abuja, Nigeria | Workshop | Workshop Day 3: Present research findings | Chike Oladipo, Jane Doe (remote), 2 NSE staff, 15 girls ages 12-15 | Increased public speaking and information synthesis capacity.
Post-Implementation Wrap-Up Period
2022-08-14 | Online | Debrief | Project team will debrief on lessons learned and plan Oklahoma City presentation outline | Chike Oladipo, Jane Doe, 2 NSE staff | Plan for next steps and outline for Capital Start-up Works presentation.
2022-09-01 | Online | Skills-sharing Event | Present videos and lessons learned to start-up employees working on computer literacy education at Capital Start-up Works event via Zoom | Jane Doe, 50 start-up employees working on computer literacy education | Increased knowledge of Nigerian context.
By September 15, 2022 | Online | Grant Requirement | Submit final report to IREX | Jane Doe, Chike Oladipo
PROJECT TEAM/STAKEHOLDERS
List the individuals and organizations who will implement the project and the roles they will play.
Individual/Organization Name | Title/Description | Role
Jane Doe | Reciprocal Exchange Participant | Project Organizer
Chike Oladipo | Reciprocal Exchange Fellowship Alumni Collaborator Collaborator | Project Organizer
Capital Start-up Works | U.S. Partner Organization | Provide event space and curriculum development support
Jenny Doe | Partner, Capital Start-up Works | Intro to coding trainer
Nigerian Society of Engineers | Nigerian Partner Organization | Provide event space and networking support

## DO NOT TOUCH (hidden)
Project Type
In-Person
Hybrid