## Guidelines
LINC Grant Work Plan Guidelines
The work plan template is in view-only mode. You will need to download the document to your computer in order to edit it for your purposes. To download the document, go to "File" in the upper left hand corner, click "Download As", select "Microsoft Excel (.xlsx)". * Please save all files consistently including your names and country of travel.
Your initial work plan may be broad but please provide your anticipated schedule and a general idea of the content of each specific activity. Add rows if necessary so that each activity, including those on the same day, is included in the plan.
Collaboration Dates: | Activity dates must be between June 1 - November 30, 2024
Strategic Priority Area(s): | LINC collaborations must relate to one or more of the following strategic priority areas: - o Cultivating Economic Prosperity and Inclusion for Marginalized and Underrepresented Groups o Fostering International Trade through Business Partnerships o Advancing Peace through Conflict Prevention and Reconciliation o Promoting Access to Quality Education with workforce preparation/job training o Innovating in Science & Technology o Promoting Inclusion through Disability Rights Advocacy o Addressing the Impact of Climate Change o Promoting Good Governance o Fostering the Development of the Creative Economy o Public Health (Public Health projects may not include direct patient care)
Collaboration Format: | In-Person or Hybrid collaborations must comply with all local COVID-19 restrictions and social distancing guidelines.Team Leads and Collaborators are required to look up the social distancing and health guidelines in the collaboration country and explain how they are addressing them in their collaboration. All in-person activities will be subject to the approval of the U.S. Department of State and U.S. Embassy/Consulate in the relevant country.
Collaboration Location: | Indicate where project activities will take place. For In-Person collaborations, list the traveler's destination country. For Hybrid collaborations, list 'Online' and the cities/countries where any in-person components will take place.
Planning, Implementation, and Wrap-Up Periods: | Organize your work plan by activities you will undertake to plan, implement, and conclude/share your project.
Collaboration Description: | Briefly describe the purpose of your collaboration and its goal. Statements should summarize activities and broadly describe the knowledge, skills, or values you want your collaboration to impart.
Activity Type: | Broadly describe the type of activities you will undertake in each stage of your collaboration. Activity types could include: meetings, site visits, trainings, etc.
Activity Description: | Broadly describe what will take place during each activity.
Number and Type of Participants: | Describe who will participate in each activity. Be as specific as possible (e.g.,Team Lead and Collaborator, university students, elementary school teachers, local community members, etc.).
Cost Coordination: | Proposals must clearly justify activity expenses and indicate the party responsible for payment in their budgets and work plans. Indicate how payments for collaboration costs will be coordinated in Column F.
Activity Outcome (Implementation Period only) | Complete this section for the Implementation Period only. Describe what you want participants to take away from each activity (e.g., a new skill or approach).

## Work Plan Template
LINC Grant Work Plan
Team Lead Name, Country: |  | Collaboration Description:
Collaborator Name, Country:
Collaboration Format (In-Person, Virtual, Hybrid)
Traveler Name (for In-Person collaboration only)
Collaboration Location(s) - City/Cities, Country:
Collaboration Dates:
Strategic Priority Area(s):
WORK PLAN
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Planning Period
[6 weeks before collaboration start date] | Online | Grant Requirement | Submit updated work plan and budget to IREX with finalized travel/project plans
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Implementation Period
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Wrap-Up Period
[Within 30 days of completed travel] | Online | Grant Requirement | Submit final report to IREX
Social Distancing Guidelines
In-Person or Hybrid collaborations must comply with all local COVID-19 restrictions and social distancing guidelines. Team Leads and Collaborators are required to look up the social distancing and health guidelines in the collaboration country and explain how they are addressing them in their project.
Guideline | Accomodation | Description of Team Member Responsibilities
What is the local COVID-19 guideline? | How will you comply with this guideline in your LINC collaboration? | How will Team Members ensure compliance?

## Example 1- In-Person
LINC Grant Example Work Plan - In-Person Collaboration
Team Lead Name, Country: | Joao Frio, Guinea Bissau | Collaboration Description: | Joao will visit Manuela's NGO, Iniciativa Para Criancas Cultivadas (Cultured Kids Initiative-ICC), to participate in its English Training in Rural Environments (ETRE) program, observe site visits to partner schools, conduct stakeholder meetings, engage with American Corner members and exchange Alumni, and collaborate on a two day workshop for secondary school teachers and administrators. Activities will comply with all local COVID-19 restrictions and social distancing guidelines. The goal of this project is to identify best practices for teaching English in remote areas, share resources on ESL training for Portuguese speakers, and help Joao's organization (Crescer Bissau) replicate the ETRE model in Guinea Bissau and increase its ability to attract funding and partners.
Collaborator Name, Country: | Manuela Goncalves, Mozambique
Collaboration Format (In-Person, Virtual, Hybrid) | In -Person
Traveler Name (for In-Person collaboration only) | Joao Frio
Collaboration Location(s) - City/Cities, Country: | Maputo, Mozambique
Collaboration Dates: | June 24 - July 9, 2024
Strategic Priority Area(s): | Promoting Access to Quality Education
WORK PLAN
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Planning Period
April 2023 | Bissau, Guinea Bissau and Maputo Mozambique | Contract Signing | Finalize MOU between ICC and Crescer Bissau | Joao and Manuela | N/A
May 2023 | Online | Grant Requirement | Submit updated work plan and budget to IREX with finalized travel/project plans | Joao and Manuela | N/A
May 2023 | Bissau, Guinea Bissau and Maputo Mozambique | Curriculum Design | Create workshop curriculum | Joao and Manuela | N/A
May 2023 | Maputo, Mozambique | Event Preparation | Finalize logistical preparations for workshop (confirm space, arrange meals, design event promotion materials, coordinate necessary COVID-19 preparations, consult with Embassy/Consulate, etc.) | Manuela | Manuela will be responsible for making and paying for all local arrangements for the workshop, including hotel and equipment rental, supplies, participant transport, etc.
May 2023 | Bissau, Guinea Bissau | Travel Planning | Purchase flight, get vaccinations, make travel arrangements | Joao | Joao will be responsible for international travel costs.
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Implementation Period
June 24 | Maputo, Mozambique | Travel | Arrival in Maputo from Bissau | Joao Frio | Joao will stay with Manuela and her family during the collaboration period. Joao will cover his own costs for food and local transportation within Maputo. | N/A
June 25, 8:30-5pm | Maputo, ICC Office | Meeting | Manuela and ICC staff will give Joao a briefing on ICC's structure, programs, and fundraising and partnership approach. Staff will review the ETRE curriculum and discuss the partners involved in its development and implementation. Joao will present Crescer Bissau's business model, training approach and materials and work with Manuela and ICC's head curriculum developer to refine them. | Joao and Manuela, ICC staff | N/A | Joao receives critical feedback on Crescer Bissau's business and training model and gains a better understanding of NGO management in order to professionalize his operations and attract more funding and partners. ICC will gain new ideas for adapting English language training to rural contexts. Training materials for the workshop will be identified and refined.
June 26, 9:30 am | Maputo, Ministerio da Educacao | Stakeholder Meeting | Meeting with Administrator for Secondary School English to discuss the Ministry's partnership on the ETRE program. | Joao and Manuela, Ministry of Education official | N/A | Joao is able to identify strategies for engagement with his own government in Guinea Bissau.
June 26, 11:30-12:30 | Maputo, British Council | Stakeholder Meeting | Meeting to discuss British Council's partnership in the development of the ETRE curriculum and their resources for other Lusophone countries. | Joao and Manuela, British Council staff | N/A | Joao is able to identify strategies for engagement with the British Council responsible for Guinea Bissau, and identify online resources his organization can utilize.
June 27, 1:30-4:30 | Maputo, American Cultural Center (ACC) | Meeting and Presentation | Meeting with ACC staff to discuss U.S. Embassy's English language learning programs. Joao and Manuela will then meet with the ACC English Club to give a presentation on "Learning English Around the World", with Mandela Washington Fellowship and TEA Alumni and English Language Fellow. | Joao and Manuela, ACC Staff, 1 English Language Fellow, 3 Alumni, 20 English Club members | N/A | Joao is exposed to English language learning resources and programs available through the U.S. Government and develops ideas for working with the American Corner in Guinea Bissau. English teacher exchange Alumni begin to cultivate a professional network. English Club members increase their cultural awareness and appreciation of the value of learning English.
June 30, 8:00-6pm | Boane and Namaacha rural secondary schools | Site Visit | Joao will join ICC's monthly site visit to partner schools in two rural districts to observe the ETRE curriculum being taught and interview school administrators, teachers, district officials, and community leaders about its implementation. | Joao and Manuela, 160 secondary school children, 12 secondary school teachers and administrators, 6 community leaders, ICC ETRE staff | Transport will be provided by ICC | Joao is able to see how the ETRE curriculum is applied and collect stakeholder feedback to inform his program's development.
July 1, 6:00-6pm | Magude and Mananga rural secondary schools | Site Visit | Joao will join ICC's monthly site visit to partner schools in two rural districts to observe the ETRE curriculum being taught and interview school administrators, teachers, district officials, and community leaders about its implementation. | Joao and Manuela, 100 secondary school children, 8 secondary school teachers and administrators, 4 community leaders | Transport will be provided by ICC | Joao is able to see how the ETRE curriculum is applied and collect stakeholder feedback to inform his program's development.
July 2 - 5 | Maputo, ICC Office | Rehearsal | Workshop rehearsal and final preparation. | Joao and Manuela, ICC staff | N/A | Workshop materials will be finalized, facilitator roles assigned, and all logistical arrangements reviewed.
July 6 - 7 | Maputo, Girassol Indy Village Hotel | Workshop | Workshop. Joao and Manuela will lead an interactive 2-day workshop on context-responsive teaching, offering strategies and resources for teaching English in rural environments. Workshop will target school teachers working in ETRE-partner schools in remote, rural areas of Maputo Province and expose them to best-practices and resources from Mozambique and Guinea Bissau. Day 1 will focus on ICC's ETRE model and will be moderated by Manuela. Joao will moderate Day 2 using Crescer Bissau's training toolkit. | Joao and Manuela, ICC ETRE staff, 25 school teachers from partner schools, 5 community leaders and education administrators, local media | Manuela will be responsible for making and paying for all local arrangements for the workshop, including hotel and equipment rental, supplies, participant transport, etc. | Workshop participants increase their capacity to deliver creative, relevant, and culturally appropriate English training to their students in rural areas. Joao is able to introduce Crescer Bissau's English teaching materials to an international audience.
July 8 | Maputo, ICC Office | Meeting | Debriefing to discuss workshop feedback, lessons learned from the collaboration, and outline a 'virtual mentoring' partnership between ICC and Crescer Bissau. | Joao and Manuela, ICC staff, Crescer Bissau Deputy Director (remotely) | N/A | Workshop feedback is documented and ICC and Crescer Bissau define a path for continued engagement .
July 9 | Maputo, Mozambique | Travel | Travel from Maputo to Bissau | Joao | Joao will pay for taxi to airport. | N/A
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Wrap-Up Period
by July 9 | Online | Grant Requirement | Submit Final Report to IREX | Joao and Manuela | N/A
Social Distancing Guidelines
In-Person or Hybrid collaborations must comply with all local COVID-19 restrictions and social distancing guidelines. Team Leads and Collaborators are required to look up the social distancing and health guidelines in the collaboration country and explain how they are addressing them in their project.
Guideline | Accomodation | Description of Team Member Responsibilities
Personal Protective Equipment is required in public and at indoor events | Masks, hand sanitizer, and gloves will be purchased and provided to all workshop participants | Manuela Goncalves will purchase with grant funds and bring to the workshop venue. Both Manuela Goncalves and Joao Frio will wear masks at for all in-person site visits and meetings
Social distancing of at least 6 ft. must be observed | Tables in the workshop venue will be spaced apart and only 2 participants will be seated at opposite ends of each table. Name tags will prevent movement. | Both Joao Frio and Manuela Goncalves will organize at the venue
25% capacity indoors | All workshop participants will need to register and numbers will be carefully monitored to ensure that it does not exceed capacity or 25%, other participants will participate remotely | Joao Frio will monitor registrations and close it once capacity has been reached. Both Joao Frio and Manuela Goncalves will monitor participant entry on the day-of entrance to ensure that the venue doesn't exceed 25%

## Example 2-Hybrid
LINC Grant Example Work Plan - Hybrid Collaboration
Team Lead Name, Country: | Joao Frio, Guinea Bissau | Collaboration Description: | Joao and Manuela will collaborate on a two-day workshop on teaching English in remote areas, targeting secondary school teachers and administrators working with Manuela's NGO, Iniciativa Para Criancas Cultivadas (Cultured Kids Initiative-ICC). Manuela will convene workshop participants in-person to present on ICC's English Training in Rural Environments (ETRE) programs. Joao will co-facilitate the session remotely, provide training materials from his organization (Crescer Bissau), and lead a virtual site visit to Crescer Bissau's community learning center to demonstrate the teaching methods in practice. Joao will provide two days of virtual consultation sessions with the workshop participants afterwards to assist them in drafting implementation plans for their own community learning centers and answer questions on Crescer Bissau's community learning model. All in-person activities will comply with all local COVID-19 restrictions and social distancing guidelines. The goal of this project is to identify best practices for teaching English in remote areas, share resources on ESL training for Portuguese speakers, build the community of English educators in Lusophone Africa, and help Joao and Manuela's organizations to attract partners.
Collaborator Name, Country: | Manuela Goncalves, Mozambique
Collaboration Format (In-Person, Virtual, Hybrid) | Hybrid
Traveler Name (for In-Person collaboration only) | N/A
Collaboration Location(s) - City/Cities, Country: | Online and Maputo, Mozambique
Collaboration Dates: | June 24 - July 2, 2024
Strategic Priority Area(s): | Promoting Access to Quality Education
WORK PLAN
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Planning Period
April 2023 | Bissau, Guinea Bissau and Maputo Mozambique | Contract Signing | Finalize MOU between ICC and Crescer Bissau | Joao and Manuela | N/A
May 2023 | Online | Grant Requirement | Submit updated work plan and budget to IREX with finalized travel/project plans | Joao and Manuela | N/A
May 2023 | Bissau, Guinea Bissau and Maputo Mozambique | Curriculum Design | Create workshop curriculum | Joao and Manuela | N/A
May 2023 | Maputo, Mozambique | Event Preparation | Finalize logistical preparations for workshop (confirm space, arrange meals, design event promotion materials, coordinate necessary COVID-19 preparations, consult with Embassy/Consulate, etc.) | Manuela | Manuela will be responsible for making and paying for all local arrangements for the workshop, including hotel and equipment rental, supplies, participant transport, etc.
May 2023 | Bissau, Guinea Bissau | Shipping | Joao will ship training materials from Guinea Bissau to Mozambique. | Joao | Joao will be responsible for shipping costs.
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Implementation Period
June 24 - 27 | Online | Stakeholder Meetings | Zoom meetings with ICC and Crescer Bissau's partners to promote the workshop, identify resources to share with participants, and discuss opportunities for cross-country collaboration in the future. | Joao, Manuela, Mozambican and Guinea-Bissauan NGOs, Ministry of Education representatives from Mozambique and Guinea Bissau, American Corner Directors | N/A | Joao and Manuela are able to identify learning resources they can share with conference participants and strategies for future engagement with civil society and government partners.
June 27 | Online and Maputo, Mozambique | Rehearsal | Technical rehearsal and final preparations for Workshop | Joao, Manuela, ICC and Crescer Bissau staff | N/A | All logistical arrangements will be reviewed, equipment tested, and support roles assigned.
June 28 - 29, 11:00-3:00 | Maputo, Mozambique and Online via Zoom | Workshop | Workshop. Joao and Manuela will lead an interactive 2-day workshop on context-responsive teaching, offering strategies and resources for teaching English in rural environments. Workshop will target school teachers and administrators from ICC's network and expose them to best-practices and resources from Mozambique and Guinea Bissau. Day 1 will focus on ICC's ETRE model and will be moderated by Manuela. Joao will moderate Day 2 using Crescer Bissau's training toolkit and host a virtual site visit to Crescer Bissau's community learning center. | Joao and Manuela, ICC ETRE staff, Crescer Bissau staff, 25 school teachers and administrators from partner schools | Manuela will be responsible for making and paying for all local arrangements for the workshop, including hotel and equipment rental, supplies, participant transport, etc. Joao will be responsible for the equipment and production costs for the virtual segments in Guinea Bissau and the shipment of training materials. Both parties will purchase Wi-Fi boosters to improve their internet connection for the event. | Workshop participants increase their capacity to deliver creative, relevant, and culturally appropriate English training to their students in rural areas. Joao is able to introduce Crescer Bissau's teaching materials and work to an international audience.
May 30 - July 1 | Online via Zoom | Consultations | Joao hosts individual consultations with workshop participants to draft implementation plans for community learning centers in their own communities. | Joao and Manuela, ICC staff, 25 school teachers and administrators from partner schools | N/A | Workshop participants receive practical guidance to replicate Crescer Bissau's community learning model in their own communities. Joao and Manuela cultivate partnerships between Crescer Bissau and the ICC educator network in Mozambique.
July 2 | Online via Zoom | Meeting | Debriefing to discuss workshop feedback, lessons learned from the collaboration, and outline a 'virtual mentoring' partnership between ICC and Crescer Bissau. | Joao and Manuela, ICC staff, Crescer Bissau staff | N/A | Workshop feedback is documented and ICC and Crescer Bissau define a path for continued engagement .
Date and Estimated Time | Location (City and Venue) | Activity Type | Activity Description | Number and Type of Participants | Cost Coordination | Activity Outcome
Wrap-Up Period
by August 1 | Online | Grant Requirement | Submit Final Report to IREX | Joao and Manuela
Social Distancing Guidelines
In-Person or Hybrid collaborations must comply with all local COVID-19 restrictions and social distancing guidelines. Team Leads and Collaborators are required to look up the social distancing and health guidelines in the collaboration country and explain how they are addressing them in their project.
Guideline | Accomodation | Description of Team Member Responsibilities
Personal Protective Equipment is required in public and at indoor events | Masks, hand sanitizer, and gloves will be purchased and provided to all workshop participants | Manuela Goncalves will purchase with grant funds and and bring to venue
Social distancing of at least 6 ft. must be observed | Tables in the venue will be spaced apart and only 2 participants will be seated at opposite ends of each table. Name tags will prevent movement. | Manuela Goncalves will organize at the venue
25% capacity indoors | All workshop participants will need to register and numbers will be carefully monitored to ensure that it does not exceed capacity or 25%, other participants will participate remotely | Joao Frio will remotely monitor registrations and close it once capacity has been reached. Manuela Goncalves will monitor participant entry on the day-of entrance to ensure that the venue doesn't exceed 25%